Workforce & Task Manager OS

Project Plan, Time Estimate & Token Budget

Date: 11 October 2026

Prepared by: komol.sokrio@gmail.com (with Claude Code)

Project folder: workforce-&-task-manager-os/task-manger

Source plan files: .claude/plan/08-current-scope.md, 09-init-scope.md, 10-final-goal.md

Contents

1. Executive summary

2. Scope

2.1 In scope — final goal

2.2 Out of scope (shown as "Soon" in the sidebar)

3. Architecture

3.1 Data models (16)

3.2 Roles

4. Work breakdown

4.1 Phase 1 — Init (foundation)

4.2 Phase 2 — Final goal (vertical slices: API + screen together)

4.3 Totals

5. Day-by-day schedule

6. Token budget

6.1 Optimized vs. unoptimized

6.2 Token rules (used in every session)

7. Risks and decisions

8. Definition of done

9. How to run the plan

# 1. Executive summary

This project rebuilds the AI-Studio mock (task-manger-moc) as a real full-stack application: an Express 5 + MongoDB backend and a Vite + React 19 + TypeScript + Tailwind 4 frontend, structured like the SE331 capstone example. The mock is used for visuals only; all data, rules, authentication and permissions are real.

The final goal is 7 working screens plus the shared shell (login, logout, profile, sidebar, topbar), built on a multi-tenant, role-based (RBAC) backend with a seeded demo database.

| Measure | Estimate |
| --- | --- |
| Total effort with Claude Code (incl. your review and testing) | ≈ 28–30 hours |
| Calendar time with Claude Code | 4–5 working days |
| Total effort by hand (one developer, no AI) | ≈ 19 developer-days |
| Claude sessions | 15 (one per step) |
| Messages (turns) | ≈ 450 |
| Total input processed (≈ 90% from cache) | ≈ 31 million tokens |
| New content read (files, command output) | ≈ 140k tokens |
| Output written (code + reasoning) | ≈ 370k tokens |
| Saving vs. an unoptimized workflow | ≈ 2.5× fewer tokens |

All time and token figures are planning estimates. Check them against real usage after step I2 and adjust if they differ by more than about 30%.

# 2. Scope

## 2.1 In scope — final goal

| Screen | What it does | Step |
| --- | --- | --- |
| Login / Logout / Profile / Sidebar / Topbar | JWT login, session restore, profile edit + password change, role-based sidebar with live badges, tenant switch (Super Admin) | I4–I5 |
| Configuration | Idle threshold, working hours/days, deadlines, leave allowances, organization profile | F1 |
| Org & Spatie RBAC | Org tree (tenant → departments → teams → members), editable permission matrix, roles with data scope | F2 |
| Task Presets | Preset CRUD, publish/unpublish; also the Tasks backend API used by other screens | F3 |
| Leave & Holidays | Balances, apply with working-day preview, 2-stage approval, holidays calendar, policies from settings | F4 |
| Time Tracker | Server-side timer, idle detection, weekly timesheet grid, manual logs, submit/approve, CSV export | F5 |
| User-wise Log | Filterable task/time log per user with CSV export and print view | F6 |
| Overview (Dashboard) | My / Team tabs: hours, attendance, task progress, salary estimate, live member tracker | F7 |

## 2.2 Out of scope (shown as "Soon" in the sidebar)

- My Tasks screen — the Tasks API is still built in F3 because Time Tracker, User-wise Log and Overview need it. Adding the screen later is about one extra session.

- Monthly Planning, HR & Attendance, Approvals & Reviews, Payroll & Payslips, Analytics & Reports.

- Attendance and Payroll data are seeded only, so the Overview cards have real numbers.

- File uploads: certificates and proofs store a file name or link only.

# 3. Architecture

| Layer | Technology / decision |
| --- | --- |
| Backend | Express 5, CommonJS JavaScript, Mongoose — layering route → controller → model-functions file → schema (SE331 style) |
| Frontend | Vite + React 19 + TypeScript + Tailwind 4, axios, react-router-dom, lucide-react; mock components reused |
| Database | Local MongoDB: mongodb://127.0.0.1:27017/workforce_os |
| Auth | JWT (Bearer) + bcryptjs; tenant always taken from the logged-in user |
| RBAC | Per-tenant roles holding permission keys; authorize(perm) middleware; data scope self / team / department / tenant |
| Multi-tenancy | Every query filtered by tenant; other-tenant records return 404; only Super Admin may switch tenant |
| API envelope | { success, data, count?, message? } |
| Runtime | Node 22 (.nvmrc); backend :5000, frontend :5173 with /api proxy |

## 3.1 Data models (16)

Tenant, User, Role, Department (teams embedded), Task, TaskPreset, TimeEntry, Timesheet, ActiveTimer, LeaveRequest, LeaveBalance, Holiday, Notification, Setting, Attendance (read-only), Payroll (read-only).

## 3.2 Roles

Super Admin, Admin, HR, Manager, Member — created per tenant by the seeder. Default scopes: Member = self, Manager = team, HR / Admin / Super Admin = tenant.

# 4. Work breakdown

## 4.1 Phase 1 — Init (foundation)

| Step | Work | Done when (gate) | By hand | With Claude |
| --- | --- | --- | --- | --- |
| I0 | Setup: git, Node 22, scaffold backend and frontend | Both dev servers start; first commit | 0.5 d | 0.5 h |
| I1 | Backend structure: server, app, db, error handler, logger, permissions, health route | GET /api/health returns success | 0.5 d | 1 h |
| I2 | All 16 models + data-access files (tenant first) | One doc per model round-trips; JSON shows id | 1 d | 2 h |
| I3 | Seeder: 3 tenants, roles, users per role, demo data, 60 days attendance, 2 months payroll | Seeding twice gives same counts | 1 d | 2 h |
| I4 | Auth API: login, me, profile, password, logout, protect / tenantScope / authorize, badges | 401 / 403 checks pass | 1 d | 1.5 h |
| I5 | Frontend shell: router, AuthContext, Login, Sidebar, Topbar, Profile modal, Logout, feature flags | Each role sees the right sidebar; refresh keeps session | 1.5 d | 2.5 h |
| I6 | Port the 7 goal views + their modals (UI only, empty/loading/error states) | All routes render; build passes; no fake data | 1.5 d | 2.5 h |
|  | Init subtotal |  | 7 d | ≈ 12 h |

## 4.2 Phase 2 — Final goal (vertical slices: API + screen together)

| Step | Work | Done when (gate) | By hand | With Claude |
| --- | --- | --- | --- | --- |
| F1 | Configuration: settings + tenant API → SettingsView | Save persists; idle threshold applies at once | 0.5 d | 1 h |
| F2 | Org & RBAC: tree, departments, teams, users, matrix, roles, scope helper → OrgRbacView + modals | Revoking a permission hides buttons and API returns 403 | 2 d | 3 h |
| F3 | Task Presets CRUD + Tasks core API → TaskPresetsView | Presets CRUD works; tasks API scoped | 1 d | 1.5 h |
| F4 | Holidays, date utils, leaves (preview, rules, 2-stage approval, balances) → Leave screen | Working days correct; balance drops after HR approval | 2.25 d | 3 h |
| F5 | Time: server timer, idle, entries, weekly grid, cell edit, submit/approve → Time Tracker | Timer survives refresh; submitted week locked (409) | 2.5 d | 4 h |
| F6 | User-wise log + CSV / print → UserReportView | Totals match tasks and time entries | 0.5 d | 1 h |
| F7 | Dashboard stats (my / team) + member detail → Overview | Every card matches a hand-checked query | 1 d | 2.5 h |
| F8 | Notifications, integration tests (401/403/404/409, isolation, flows), README | Test suite green; README setup ≤ 10 commands | 2.5 d | 2.5 h |
|  | Final-goal subtotal |  | 12.25 d | ≈ 18.5 h |

## 4.3 Totals

|  | By hand | With Claude Code |
| --- | --- | --- |
| Init (I0–I6) | 7 developer-days | ≈ 12 h |
| Final goal (F1–F8) | 12.25 developer-days | ≈ 18.5 h |
| Total | ≈ 19 developer-days | ≈ 28–30 h (4–5 working days) |

# 5. Day-by-day schedule

| Day | Steps | Hours | End-of-day result |
| --- | --- | --- | --- |
| Day 1 | I0, I1, I2, I3 | ≈ 5.5 h | Backend runs, all models exist, demo database seeded |
| Day 2 | I4, I5, I6 | ≈ 6.5 h | Login works for every role; all 7 screens visible (UI only) |
| Day 3 | F1, F2, F3 | ≈ 5.5 h | Configuration, Org & RBAC and Task Presets fully working |
| Day 4 | F4, F5 | ≈ 7 h | Leave & Holidays and Time Tracker fully working |
| Day 5 | F6, F7, F8 | ≈ 6 h | User log, Overview, tests and README done — demo ready |

Each step is one Claude Code session: run /phase <step>, wait for the gate to pass, then /clear before the next step. Use /status at any time to see progress.

# 6. Token budget

Every message re-sends the whole conversation context. Most of that comes from the cache, which costs about 10% of the normal input price. What really costs is new content read (files, command output) and the code and text Claude writes.

| Step | Turns | New reads | Output | Avg context | Input processed |
| --- | --- | --- | --- | --- | --- |
| I0 Setup | 15 | 3k | 4k | 30k | 0.45M |
| I1 Backend structure | 20 | 6k | 8k | 40k | 0.80M |
| I2 Models | 25 | 5k | 18k | 50k | 1.25M |
| I3 Seeder | 25 | 6k | 15k | 55k | 1.40M |
| I4 Auth API | 25 | 5k | 10k | 50k | 1.25M |
| I5 Frontend shell | 35 | 20k | 20k | 70k | 2.45M |
| I6 Port 7 views | 35 | 23k | 15k | 80k | 2.80M |
| F1 Configuration | 20 | 4k | 8k | 45k | 0.90M |
| F2 Org & RBAC | 40 | 10k | 25k | 80k | 3.20M |
| F3 Presets + Tasks API | 25 | 5k | 12k | 55k | 1.40M |
| F4 Leave & Holidays | 40 | 12k | 25k | 85k | 3.40M |
| F5 Time Tracker | 50 | 15k | 30k | 95k | 4.75M |
| F6 User-wise Log | 20 | 6k | 10k | 55k | 1.10M |
| F7 Overview | 35 | 12k | 20k | 85k | 2.98M |
| F8 Notifications + tests | 40 | 10k | 25k | 80k | 3.20M |
| Total | ≈ 450 | ≈ 140k | ≈ 245k code (≈ 370k with reasoning) |  | ≈ 31M |

## 6.1 Optimized vs. unoptimized

|  | With token rules | Without |
| --- | --- | --- |
| New content read | ≈ 140k | ≈ 360k |
| Output (incl. reasoning) | ≈ 370k | ≈ 450k+ |
| Total input processed | ≈ 31M | ≈ 75–85M |

| Saving | Tokens saved |
| --- | --- |
| Short sessions with /clear instead of a few long ones (context past 150k) | 30–40M |
| Not carrying large files in context (full spec 7.7k, ModalRoot.tsx 17.8k) | ≈ 7M |
| Smaller CLAUDE.md load (≈ 11.5k → ≈ 2.6k per message) | ≈ 4M |
| Copying mock files with cp instead of retyping | ≈ 40k output |

## 6.2 Token rules (used in every session)

- One step per session; /clear after the gate passes and PROGRESS.md is updated.

- Read only the spec section a step names; never read the whole 08 file.

- Never read ModalRoot.tsx (17.8k) or the mock server (13.6k) whole; grep and read ranges.

- Port mock files with cp, then edit only the data lines.

- Keep command output short (| tail -30, | head -c 600).

- No subagents — each one starts cold and re-reads the plan.

- Sonnet for routine steps (I0–I6, F1, F3, F6, F8); Opus for logic-heavy steps (F2, F4, F5, F7).

- Do not re-read files just written; verify by running.

- Check /context mid-session; past ~120k, wrap up and /clear.

# 7. Risks and decisions

| # | Risk / decision | Default chosen |
| --- | --- | --- |
| R1 | Overview needs attendance and payroll data from out-of-scope modules | Read seeded data; becomes live when those modules are built |
| R2 | Approvals screen is out of scope but leave and timesheet approval are needed | Approve inside each module's own screen; the same endpoints are reused later |
| R3 | My Tasks screen is out of scope but tasks feed other screens | Build the Tasks API in F3; screen behind a "Soon" flag |
| R4 | File uploads for certificates and proofs | Store file name or link only; real upload is a stretch goal |
| R5 | Working week differs by tenant (BD Sun–Thu vs Mon–Fri) | Per-tenant setting; seeded per tenant |
| R6 | Timezone (Asia/Dhaka vs UTC) near midnight | Checked during F8 tests |
| R7 | Estimates may be off | Re-check time and tokens after I2; adjust if off by > 30% |

# 8. Definition of done

- npm run seed builds the full demo database from scratch, and running it twice gives the same result.

- Each seeded role can log in; the sidebar and API access match the permission matrix.

- All 7 screens show only database data — no hard-coded names, dates or numbers.

- Every create and approve flow persists and survives a server restart.

- Tenant A can never read or write tenant B data (covered by tests).

- Integration tests pass: 401 / 403 / 404 / 409, tenant isolation, leave, timesheet and task flows.

- README explains setup in 10 commands or fewer, with demo logins and a demo script.

# 9. How to run the plan

- Open Claude Code in the task-manger folder and run nvm use (Node 22).

- Run /phase I0. Wait until the gate passes and PROGRESS.md is updated.

- Run /clear, then the next step: I1 … I6, then F1 … F8.

- Switch model with /model: Sonnet for routine steps, Opus for F2, F4, F5, F7.

- Use /status to see progress and /seed-check to verify seeded data.